2014-04-23

1:30 p.m. ET

Teleconference

CCSD CDP Data purchase and access working group

Meeting notes

# 1. Welcome

Attendees: Brendan Rahman (CDP), Chelsea Turan (Simcoe County), Natalie Hui (York Region), Wayne Chu (Toronto), Christina Maes Nino (Winnipeg), Cheryl Hitchen (KFLA), Auburn Larose (WDG), Matt Laurie (Toronto), Debbie Belgrave (Calgary), Veronique Dryden (Peel Region), Louisa Wong (Hamilton), Clara Jimeno (Ottawa)

# 2. Update on NHS orders

- The order is working its way through Statistics Canada. It will be broken into several "contracts" so that we get a steady supply of data. Subject to confirmation from Statistics Canada, we are expecting the order to be completed by the end of September.

  - See 2011 Census and NHS order – detailed summary.xlsx for the list of tables we expect to have in-hand by the end of the summer

# 3. Custom geographies

- We have decided to order Census and NHS Profiles at custom geographies already completed.

  - See Update on custom geographies – 2014-04-23.xlsx

- We must now prioritize what other tables to order at custom geographies. If we increase the number of tables to be produced using custom geographies, we will have to reduce the overall order by a similar number of tables. Note that some tables at standard geographies will prove unfeasible to order at custom geographies.

- The tables we have agreed to order already at custom geographies (based on multiple requests and high demand generally) include:

  - NHS and Census Profiles

  - 98-311-x2011018

  - UPP Table 1

  - Target group profile of the Aboriginal population

- Big question: How do we prioritize custom geographies? Simply use the existing rating system? Ask members?

  - There is a general agreement that existing rating system is suitable.

  - Members are always welcome to provide feedback as the order progresses—we will try to accommodate changes where possible.

  - ACTION: Brendan to maintain frequent communication with Leads and WG w/r to orders (placed and received).

# 4. Things to bring up at the May 8-9 Annual Meeting

- B will provide a summary of the activities of the Working Group at the May 8-9 Annual Meeting.

- Is there anything I should bring up on the Group's behalf? Comments, grievances, praise?

  - Wayne: Explore how to make the prioritization of tables a more ongoing, streamlined process (e.g. running tally)

# 5. New catalogue

- Things we've accomplished

  - Better-structured metadata

  - Simpler, faster search filters

  - More sensible arrangement of geographies

  - Pictures

  - Direct links to externally-hosted data

- Things we still need to do

  - Translation

  - Single-click downloads

    - This is a very high priority according to working group

  - Autocompleting search bar

    - Functionality should include the ability to search by variables or ad-hoc tags (plain English)—very useful for beginners

  - Some theming / formatting

# 6. Other business

# 7. Next meeting

- Next meeting: Wednesday, May 28, 2014, at 1:30 p.m. ET.